## Overview
Project Atlas — WBS Dictionary
Project | Project Atlas
Artifact | Work Breakdown Structure Dictionary
Delivery Model | Predictive / Waterfall
Baseline Version | 1.0
Current Stage | Planning
Purpose | Define the content, ownership, acceptance, dependencies, requirements linkage, and planning assumptions for WBS work packages.
Scope Baseline | Scope Statement + WBS + WBS Dictionary
Cost Baseline / BAC | ₹2.40 Crore
Total Authorized Budget | ₹2.55 Crore
Work Package Coding | WBS IDs in this workbook will be reused by schedule, resource, budget, RAID, and EVM artifacts.
Control Principle | Material changes to baselined WBS content require integrated change control.
Portfolio Note | All project data are synthetic and used only for portfolio demonstration.
Next Planning Step | Integrated Project Schedule, followed by resource and cost planning.
KPI | Value | Meaning | Target / Note
Total Work Packages | 63 | Number of lowest-level WBS work packages | Baseline count
Control Accounts | 8 | Top-level WBS control accounts | 8
Requirements-Linked WPs | 187 | Work packages explicitly linked to RTM requirements | Monitor
Baselined WPs | 63 | Work packages currently baselined | 100%
Scope Baseline Status | Established | Scope Statement + WBS + WBS Dictionary | Established

## WBS Dictionary
WBS ID | Level 1 Control Account | Level 2 Component | Work Package | Workstream | Description / Scope of Work | Primary Deliverable(s) | Acceptance Criteria | Primary Owner | Acceptance Authority | Key Predecessor / Dependency | Related Requirement IDs | Planning Assumptions | Primary Cost Category | Schedule / Milestone Link | Status
1.1.1 | 1.0 Project Management & Governance | 1.1 Integrated Project Management | Integrated Project Management Plan | Project Management & Governance | Consolidate the subsidiary management approaches and define how Project Atlas will be planned, executed, monitored, controlled, and closed. | Integrated Project Management Plan | Core management approaches are documented, internally consistent, and accepted by the Project Manager and Sponsor. | Project Manager | Executive Sponsor | Approved Charter and Business Case | N/A | Plan will be tailored to project size and regulated delivery context. | Project Management | Planning baseline approval | Baselined
1.1.2 | 1.0 Project Management & Governance | 1.1 Integrated Project Management | Integrated Schedule & Baseline Control | Project Management & Governance | Develop, baseline, maintain, and control the integrated project schedule linked to approved scope and work packages. | Integrated Project Schedule; Schedule Baseline | Critical path, dependencies, milestones, and approved baseline are established and traceable to WBS work packages. | Project Manager | Executive Sponsor | Approved WBS and resource estimates | N/A | Detailed activity planning will follow WBS approval. | Project Management | Schedule baseline approval | Baselined
1.1.3 | 1.0 Project Management & Governance | 1.1 Integrated Project Management | Project Status & Performance Reporting | Project Management & Governance | Define and operate project reporting covering scope, schedule, cost, quality, risks, issues, dependencies, and decisions. | Weekly status pack; Monthly steering report | Reports are issued to agreed cadence and contain current performance and decision information. | Project Manager | Executive Sponsor | Baselines and project control data | N/A | Reporting frequency follows Governance Model. | Project Management | Weekly / monthly governance | Baselined
1.1.4 | 1.0 Project Management & Governance | 1.1 Integrated Project Management | RAID & Decision Management | Project Management & Governance | Maintain structured identification, ownership, response, escalation, and closure of risks, assumptions, issues, dependencies, and decisions. | RAID Register; Decision Log | Open items have owners, dates, status, response/actions, and escalation where thresholds are exceeded. | Project Manager | Executive Sponsor | Stakeholder and workstream inputs | N/A | RAID reviews occur at weekly and fortnightly governance cadence. | Project Management | Ongoing project control | Baselined
1.1.5 | 1.0 Project Management & Governance | 1.1 Integrated Project Management | Integrated Change Control | Project Management & Governance | Assess proposed changes for impact across scope, schedule, cost, resources, quality, risk, and benefits before approval. | Change Register; Change Requests; Approved baseline updates | No material baseline change is implemented without documented impact assessment and approval. | Project Manager | Steering Committee | Approved baselines | N/A | Thresholds follow Governance Model. | Project Management | Change Control Board / Steering decisions | Baselined
1.2.1 | 1.0 Project Management & Governance | 1.2 Governance & Commercial Control | Delivery Governance Forums | Project Management & Governance | Operate weekly cross-workstream governance to review progress, dependencies, actions, and delivery blockers. | Weekly Delivery Review agenda and actions | Meeting cadence is maintained and material actions are tracked to closure. | Project Manager | Executive Sponsor | Workstream status | N/A | Workstream leads attend weekly review. | Project Management | Weekly Delivery Review | Baselined
1.2.2 | 1.0 Project Management & Governance | 1.2 Governance & Commercial Control | Steering Committee Governance | Project Management & Governance | Prepare and facilitate monthly executive governance for project health, major risks, financials, changes, and decisions. | Steering Committee pack; Decision record | Executive decisions and escalations are captured and communicated. | Project Manager | Executive Sponsor | Current project performance | N/A | Monthly steering cadence. | Project Management | Monthly Steering Committee | Baselined
1.2.3 | 1.0 Project Management & Governance | 1.2 Governance & Commercial Control | Stage-Gate Governance | Project Management & Governance | Coordinate evidence and approvals required to progress through defined lifecycle stage gates. | Stage-gate packs and approvals | Required entry/exit criteria are met or formally waived before progression. | Project Manager | Steering Committee | Lifecycle deliverables | REG-002 | Stage gates align to requirements, design, testing, release, and closure milestones. | Project Management | Lifecycle stage gates | Baselined
1.2.4 | 1.0 Project Management & Governance | 1.2 Governance & Commercial Control | Vendor & Procurement Coordination | Project Management & Governance | Coordinate procurement, onboarding, deliverables, performance, and closure for specialist external services. | Procurement plan; Vendor deliverable tracker | Required external services are available within approved scope, cost, and lead times. | Project Manager | Executive Sponsor | Approved procurement needs | N/A | External security/validation support may be procured. | External / Specialist Vendor Services | Procurement and vendor milestones | Baselined
1.2.5 | 1.0 Project Management & Governance | 1.2 Governance & Commercial Control | Financial Control & Forecasting | Project Management & Governance | Establish time-phased cost baseline and maintain actuals, commitments, forecasts, reserves, and variance analysis. | Cost Baseline; Forecast; EVM reports | Cost reporting reconciles to approved BAC and material variances have explanation and action. | Project Manager | Executive Sponsor | WBS, schedule, resource and procurement estimates | N/A | BAC is ₹2.40 Cr; management reserve held outside baseline. | Project Management | Cost baseline and monthly forecast | Baselined
2.1.1 | 2.0 Requirements & Solution Design | 2.1 Requirements Baseline | Business & Functional Requirements | Requirements & Solution Design | Elicit, document, review, and baseline business and functional requirements for the replacement application. | Approved business and functional requirements | Requirements are clear, testable, traceable, and approved by designated business authority. | Business Analysis Lead | Business Owner | Business Case and stakeholder inputs | BUS-001,BUS-002,BUS-003,FUN-001–FUN-005 | Business SMEs are available for workshops and approvals. | Internal / Contract Resources | Requirements Baseline | Baselined
2.1.2 | 2.0 Requirements & Solution Design | 2.1 Requirements Baseline | Integration & Data Requirements | Requirements & Solution Design | Define interface, data, migration, reconciliation, and retention requirements. | Approved integration and data requirements | All four interfaces and required migration scope have approved, testable requirements. | Business Analysis Lead | Technology Lead | Enterprise integration and data-owner inputs | INT-001–INT-004,DAT-001–DAT-003 | Interface owners will confirm specifications within planning window. | Internal / Contract Resources | Requirements Baseline | Baselined
2.1.3 | 2.0 Requirements & Solution Design | 2.1 Requirements Baseline | Regulatory, Security & Non-Functional Requirements | Requirements & Solution Design | Define compliance, security, performance, availability, operational, and training requirements. | Approved regulatory, security, NFR and operational requirements | Control requirements are measurable and approved by relevant authorities. | Business Analysis Lead | Quality / Compliance | Quality, security and operations inputs | REG-001–REG-002,SEC-001–SEC-003,NFR-001–NFR-003,OPS-001–OPS-003,TRN-001–TRN-002 | Enterprise standards remain applicable throughout design. | Internal / Contract Resources | Requirements Baseline | Baselined
2.1.4 | 2.0 Requirements & Solution Design | 2.1 Requirements Baseline | Requirements Traceability & Baseline Approval | Requirements & Solution Design | Establish traceability between business need, requirement, design, verification, and acceptance; secure baseline approval. | Requirements Traceability Matrix; Requirements approval | Baseline requirements have unique IDs, acceptance criteria, owners, verification methods, and approval status. | Business Analysis Lead | Business Owner | 2.1.1–2.1.3 | All baseline requirements | RTM is maintained under change control after approval. | Internal / Contract Resources | Requirements Baseline | Baselined
2.2.1 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Application Solution Design | Requirements & Solution Design | Develop the target application design covering workflows, business rules, reporting, audit, and application components. | Application Solution Design | Design addresses approved application requirements and passes formal design review. | Solution Architect | Technology Lead | 2.1 Requirements Baseline | BUS-001–BUS-003,FUN-001–FUN-005 | Existing enterprise architecture standards are used. | Internal / Contract Resources | Solution Design Approval | Baselined
2.2.2 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Integration Solution Design | Requirements & Solution Design | Define interface patterns, mappings, error handling, monitoring, and technical dependencies for four integrations. | Integration Design Specification | All four integration designs are approved by application and enterprise integration owners. | Integration & Data Migration Lead | Technology Lead | 2.1.2 | INT-001–INT-004 | Connected systems expose approved integration mechanisms. | Internal / Contract Resources | Solution Design Approval | Baselined
2.2.3 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Data Migration Design | Requirements & Solution Design | Define source-to-target mapping, transformation, cleansing, reconciliation, migration sequencing, and evidence requirements. | Data Migration Design & Reconciliation Approach | Migration approach covers active/historical scope and approved reconciliation controls. | Integration & Data Migration Lead | Technology Lead | 2.1.2 | DAT-001–DAT-003 | Source data is accessible for profiling. | Internal / Contract Resources | Solution Design Approval | Baselined
2.2.4 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Security & Access Design | Requirements & Solution Design | Define role model, least-privilege access, authentication, encryption, logging, and security controls. | Security & Access Design | Information Security approves the control design and identified risks have disposition. | Solution Architect | Information Security | 2.1.3 | SEC-001–SEC-003,BUS-002 | Enterprise IAM and security standards are available. | Internal / Contract Resources | Security Design Review | Baselined
2.2.5 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Operational & Support Design | Requirements & Solution Design | Define monitoring, alerting, support ownership, recovery, known-error handling, and operational procedures. | Operational Support Design | Operations confirms support model and monitoring/recovery requirements are implementable. | Solution Architect | Operations Lead | 2.1.3 | NFR-003,OPS-001–OPS-003 | BAU support team participates in design review. | Internal / Contract Resources | Operational Design Review | Baselined
2.2.6 | 2.0 Requirements & Solution Design | 2.2 Solution Design | Solution Design Approval | Requirements & Solution Design | Consolidate design evidence and secure formal technical, security, quality, and operational approval to begin full build. | Approved Solution Design Pack | All mandatory design comments are resolved or formally dispositioned. | Solution Architect | Technology Lead | 2.2.1–2.2.5 | All relevant requirements | Design approval is a formal stage gate. | Internal / Contract Resources | Solution Design Approval | Baselined
3.1.1 | 3.0 Application Development | 3.1 Application Foundation | Application Framework & Configuration | Application Development | Configure the application foundation, environments, base components, workflow framework, logging, and common services. | Configured application foundation | Foundation is deployable to development/test environment and meets approved architecture standards. | Application Development Lead | Technology Lead | 2.2.6 | BUS-001,NFR-001–NFR-003 | Required platform licenses/environments are available. | Internal / Contract Resources | Build Complete | Baselined
3.1.2 | 3.0 Application Development | 3.1 Application Foundation | Role-Based Access Implementation | Application Development | Implement role profiles, permission controls, authentication integration hooks, and audit-related access controls. | Configured RBAC model | Access tests demonstrate approved role permissions and least-privilege behavior. | Application Development Lead | Information Security | 2.2.4,3.1.1 | SEC-001,INT-001,BUS-002 | Role matrix is approved before final configuration. | Internal / Contract Resources | Build Complete | Baselined
3.2.1 | 3.0 Application Development | 3.2 Business Workflow Features | Record Management Workflow | Application Development | Develop core create, review, update, submit, and status-management functionality for regulated records. | Record management feature set | Approved end-to-end workflow scenarios execute successfully in developer verification. | Application Development Lead | Business Owner | 3.1.1,2.2.1 | BUS-001,FUN-001 | Business rules remain stable after design approval. | Internal / Contract Resources | Build Complete | Baselined
3.2.2 | 3.0 Application Development | 3.2 Business Workflow Features | Approval Routing & Business Rules | Application Development | Implement configurable approvals, routing logic, validation rules, and workflow-state transitions. | Approval routing and business-rule features | Approved routing scenarios produce expected decisions and audit events. | Application Development Lead | Business Owner | 3.2.1 | FUN-002,BUS-002 | Approval hierarchy is provided by Business Owner. | Internal / Contract Resources | Build Complete | Baselined
3.2.3 | 3.0 Application Development | 3.2 Business Workflow Features | Search, Reporting & Audit Features | Application Development | Implement approved search, filtering, operational reporting, audit display, and retrieval capabilities. | Search/reporting/audit feature set | Search and reports meet approved functional and data-accuracy criteria. | Application Development Lead | Business Owner | 3.2.1 | FUN-003,FUN-004,BUS-002 | Reporting uses approved operational data model. | Internal / Contract Resources | Build Complete | Baselined
3.2.4 | 3.0 Application Development | 3.2 Business Workflow Features | Workflow Notifications | Application Development | Implement workflow-trigger logic and notification payload generation for designated business events. | Notification feature configuration | Configured workflow events generate correct notification requests without duplicates. | Application Development Lead | Business Owner | 3.2.2,2.2.2 | FUN-005,INT-004 | Enterprise Notification service remains available for integration testing. | Internal / Contract Resources | Build Complete | Baselined
3.3.1 | 3.0 Application Development | 3.3 Application Release Candidate | Developer Verification & Code Quality | Application Development | Complete unit/developer verification, static/code-quality checks, defect remediation, and release readiness for formal testing. | Developer verification evidence; Code-quality results | No open blocker defects and defined code-quality thresholds are met. | Application Development Lead | Technology Lead | 3.1–3.2 work packages | All application requirements | Development team follows enterprise engineering standards. | Internal / Contract Resources | Build Complete | Baselined
3.3.2 | 3.0 Application Development | 3.3 Application Release Candidate | Application Release Candidate Package | Application Development | Package the approved application build and supporting technical documentation for controlled testing. | Release candidate build and release notes | Release candidate is deployable to the controlled test environment and configuration is versioned. | Application Development Lead | Technology Lead | 3.3.1 | All application requirements | Configuration management process is available. | Software & Licensing | Build Complete | Baselined
4.1.1 | 4.0 Integration & Data Migration | 4.1 Enterprise Integrations | Identity & Access Management Integration | Integration & Data Migration | Build and configure authentication/identity integration with enterprise IAM. | IAM integration | Approved users authenticate successfully and unauthorized users are rejected during integration testing. | Integration & Data Migration Lead | Information Security | 2.2.2,2.2.4,3.1.2 | INT-001,SEC-001 | Enterprise IAM interface is available. | Internal / Contract Resources | Integration Build Complete | Baselined
4.1.2 | 4.0 Integration & Data Migration | 4.1 Enterprise Integrations | Enterprise Master Data Integration | Integration & Data Migration | Build interface to retrieve required reference/master data from enterprise service. | Master Data integration | Approved reference entities are received and mapped accurately. | Integration & Data Migration Lead | Technology Lead | 2.2.2 | INT-002 | Enterprise Master Data service supports agreed interface. | Internal / Contract Resources | Integration Build Complete | Baselined
4.1.3 | 4.0 Integration & Data Migration | 4.1 Enterprise Integrations | Records Management Integration | Integration & Data Migration | Build transfer and retrieval linkage with enterprise records-management platform. | Records Management integration | Approved final records transfer with required metadata and are retrievable. | Integration & Data Migration Lead | Quality / Compliance | 2.2.2 | INT-003 | Records platform metadata standards remain stable. | Internal / Contract Resources | Integration Build Complete | Baselined
4.1.4 | 4.0 Integration & Data Migration | 4.1 Enterprise Integrations | Enterprise Notification Integration | Integration & Data Migration | Build integration to enterprise notification service for configured workflow events. | Notification integration | Messages are delivered for configured events with correct payload and no duplicate delivery. | Integration & Data Migration Lead | Technology Lead | 2.2.2,3.2.4 | INT-004,FUN-005 | Notification service supports agreed throughput. | Internal / Contract Resources | Integration Build Complete | Baselined
4.2.1 | 4.0 Integration & Data Migration | 4.2 Data Migration | Source Data Profiling & Mapping | Integration & Data Migration | Profile source data and establish approved source-to-target mapping, quality findings, and cleansing actions. | Data profiling report; Mapping specification | In-scope fields have approved mapping and material data-quality issues have disposition. | Integration & Data Migration Lead | Business Owner | 2.2.3 | DAT-001–DAT-003 | Source extracts are available and representative. | Internal / Contract Resources | Migration Design Complete | Baselined
4.2.2 | 4.0 Integration & Data Migration | 4.2 Data Migration | Migration Development & Reconciliation Controls | Integration & Data Migration | Develop migration routines, transformation logic, exception handling, and reconciliation controls. | Migration scripts; Reconciliation controls | Migration routines process approved sample data and reconcile to expected control totals. | Integration & Data Migration Lead | Technology Lead | 4.2.1 | DAT-001–DAT-003 | Cleansing rules are approved before final migration logic. | Internal / Contract Resources | Migration Build Complete | Baselined
4.2.3 | 4.0 Integration & Data Migration | 4.2 Data Migration | Trial Migration & Reconciliation | Integration & Data Migration | Execute controlled trial migration to validate runtime, mapping, transformations, exceptions, and reconciliation. | Trial migration results; Reconciliation report | Trial migration meets agreed completeness/accuracy thresholds and issues have remediation plans. | Integration & Data Migration Lead | Business Owner | 4.2.2, test environment readiness | DAT-001–DAT-003 | Trial data volume is representative of production. | Cloud & Infrastructure | Validation & UAT Readiness | Baselined
4.2.4 | 4.0 Integration & Data Migration | 4.2 Data Migration | Production Migration & Final Reconciliation | Integration & Data Migration | Execute production migration during approved cutover and complete final business/technical reconciliation. | Production migration evidence; Final reconciliation approval | Approved active records are migrated or formally exceptioned and reconciliation is signed off. | Integration & Data Migration Lead | Business Owner | 4.2.3,7.1.3 | DAT-001–DAT-003 | Production data freeze/cutover window is approved. | Cloud & Infrastructure | Production Go-Live | Baselined
5.1.1 | 5.0 Testing & Validation | 5.1 Test & Validation Preparation | Test & Validation Strategy | Testing & Validation | Define test levels, validation approach, entry/exit criteria, environments, defect governance, and evidence requirements. | Approved Test & Validation Strategy | Strategy addresses regulated requirements, technical verification, UAT, and traceability. | Validation & Deployment Lead | Quality / Compliance | 2.1 baseline and solution approach | REG-001,REG-002 | Quality authority participates in planning. | Validation & Security Services | Test Planning Complete | Baselined
5.1.2 | 5.0 Testing & Validation | 5.1 Test & Validation Preparation | Test Cases, Test Data & Environment Readiness | Testing & Validation | Prepare traceable test cases, representative test data, and validated test-environment readiness. | Test cases; Test data; Environment readiness confirmation | Required test coverage is mapped to RTM and environments/data are ready for execution. | Validation & Deployment Lead | Quality / Compliance | 5.1.1,2.2.6 | All baseline requirements | Environment and test-data access is available. | Validation & Security Services | System Testing Start | Baselined
5.2.1 | 5.0 Testing & Validation | 5.2 Technical Verification | System & Regression Testing | Testing & Validation | Execute system and regression tests for application features and resolved defects. | System test results; Regression results | Exit criteria are met and no unresolved blocker defects remain. | Validation & Deployment Lead | Technology Lead | 3.3.2,5.1.2 | BUS/FUN/NFR applicable requirements | Release candidate is configuration-controlled. | Validation & Security Services | System Testing Complete | Baselined
5.2.2 | 5.0 Testing & Validation | 5.2 Technical Verification | Integration Testing | Testing & Validation | Execute end-to-end integration tests across all four enterprise interfaces and error scenarios. | Integration test results | All critical interface scenarios pass or have approved disposition. | Validation & Deployment Lead | Technology Lead | 4.1.1–4.1.4,5.1.2 | INT-001–INT-004 | Connected test endpoints remain available. | Validation & Security Services | Integration Testing Complete | Baselined
5.2.3 | 5.0 Testing & Validation | 5.2 Technical Verification | Performance Testing | Testing & Validation | Validate approved concurrency, response-time, and operational performance thresholds. | Performance test report | 500-user workload and defined response thresholds meet approved NFR criteria or have accepted remediation. | Validation & Deployment Lead | Technology Lead | 5.2.1 and stable integrated build | NFR-001,NFR-002 | Performance environment is representative enough for decision-making. | Validation & Security Services | Technical Verification Complete | Baselined
5.2.4 | 5.0 Testing & Validation | 5.2 Technical Verification | Security Assessment | Testing & Validation | Execute vulnerability/security assessment and verify security controls before release. | Security assessment report | No open critical vulnerabilities and high findings have approved disposition. | Validation & Deployment Lead | Information Security | Stable integrated build | SEC-001–SEC-003 | External specialist support may be used. | Validation & Security Services | Security Approval | Baselined
5.3.1 | 5.0 Testing & Validation | 5.3 Validation & Business Acceptance | Regulated Validation Execution | Testing & Validation | Execute required validation protocols and maintain controlled evidence for designated regulated requirements. | Validation evidence package | Required validation tests pass and deviations are resolved or formally approved. | Validation & Deployment Lead | Quality / Compliance | 5.1.1,5.1.2,5.2 technical verification | REG-001,REG-002 | Validation scope is based on approved risk and requirements. | Validation & Security Services | Validation Complete | Baselined
5.3.2 | 5.0 Testing & Validation | 5.3 Validation & Business Acceptance | User Acceptance Testing | Testing & Validation | Coordinate representative business UAT across in-scope regions and workflows. | UAT results; Business acceptance | Critical business scenarios pass and Business Owner formally accepts UAT outcome. | Validation & Deployment Lead | Business Owner | 5.2.1,5.2.2,4.2.3 | BUS-001–BUS-003,FUN-001–FUN-005 | Business testers are available during planned window. | Internal / Contract Resources | UAT Complete | Baselined
5.3.3 | 5.0 Testing & Validation | 5.3 Validation & Business Acceptance | Defect Resolution & Retesting | Testing & Validation | Triage, prioritize, remediate, retest, and disposition defects from technical testing, validation, and UAT. | Defect log; Retest evidence | No Severity-1 defects remain at go-live; remaining defects have approved disposition. | Validation & Deployment Lead | Technology Lead | 5.2 and 5.3 test execution | All affected requirements | Development capacity is reserved for defect remediation. | Internal / Contract Resources | Validation & UAT Complete | Baselined
5.3.4 | 5.0 Testing & Validation | 5.3 Validation & Business Acceptance | Traceability & Validation Approval | Testing & Validation | Reconcile RTM, design references, test evidence, deviations, and approvals to demonstrate release traceability. | Final RTM; Validation approval | Designated regulated requirements have complete traceability and Quality approval. | Validation & Deployment Lead | Quality / Compliance | 5.3.1–5.3.3 | REG-001,REG-002 and all designated regulated requirements | RTM is current before production-readiness review. | Validation & Security Services | Validation & UAT Complete | Baselined
6.1.1 | 6.0 Business Readiness & Training | 6.1 Business Readiness | Business Impact & Readiness Assessment | Business Readiness & Training | Assess impacted roles, process changes, readiness risks, support needs, and regional deployment preparedness. | Business Readiness Assessment | Material readiness gaps have owners and action plans before go-live decision. | Change & Training Lead | Business Owner | Approved solution and deployment scope | BUS-003,OPS-002 | Regional representatives participate in readiness review. | Training & Change Readiness | Production Readiness | Baselined
6.1.2 | 6.0 Business Readiness & Training | 6.1 Business Readiness | Stakeholder Communications & Adoption Readiness | Business Readiness & Training | Prepare and deliver targeted communications for impacted user and leadership groups. | Communication pack; Adoption readiness actions | Planned communications are delivered and critical stakeholder concerns are resolved/escalated. | Change & Training Lead | Business Owner | Stakeholder Register and readiness assessment | BUS-003 | Communication channels are available across regions. | Training & Change Readiness | Production Readiness | Baselined
6.2.1 | 6.0 Business Readiness & Training | 6.2 Training | Training Materials & User Guidance | Business Readiness & Training | Develop role-based training materials, job aids, and user guidance aligned to the approved solution. | Training materials; User guides | Materials cover identified user roles and are approved before final UAT completion. | Change & Training Lead | Business Owner | Stable solution and workflows | TRN-001 | Screens/processes are stable enough for final materials. | Training & Change Readiness | UAT Complete | Baselined
6.2.2 | 6.0 Business Readiness & Training | 6.2 Training | User Training Delivery & Completion Tracking | Business Readiness & Training | Deliver training to priority users and monitor completion/readiness exceptions. | Training sessions; Completion tracker | At least 95% of priority users complete training or exceptions are approved. | Change & Training Lead | Business Owner | 6.2.1 | TRN-002 | Priority user population is confirmed before delivery. | Training & Change Readiness | Production Readiness | Baselined
7.1.1 | 7.0 Deployment & Hypercare | 7.1 Release Readiness | Production Readiness Assessment | Deployment & Hypercare | Assess functional, technical, security, quality, operational, training, migration, and support readiness for production. | Production Readiness Checklist | Mandatory release criteria are met or approved waivers exist. | Validation & Deployment Lead | Steering Committee | 5.3.4,6.1,6.2,4.2.3 | OPS-001–OPS-003,TRN-002 | Readiness assessment consolidates all workstreams. | Internal / Contract Resources | Production Readiness Approval | Baselined
7.1.2 | 7.0 Deployment & Hypercare | 7.1 Release Readiness | Cutover & Rollback Plan | Deployment & Hypercare | Define sequenced cutover steps, owners, timing, validation checkpoints, communications, and rollback approach. | Approved Cutover & Rollback Plan | All critical cutover tasks have owners and rollback criteria/steps are reviewed. | Validation & Deployment Lead | Technology Lead | 4.2.3,5.3.4 | OPS-003 | Production window is confirmed. | Internal / Contract Resources | Production Readiness Approval | Baselined
7.1.3 | 7.0 Deployment & Hypercare | 7.1 Release Readiness | Go / No-Go Approval | Deployment & Hypercare | Present readiness evidence and obtain formal authorization to execute production cutover. | Go / No-Go decision record | Steering Committee records decision after review of readiness, residual risks, and rollback capability. | Project Manager | Steering Committee | 7.1.1,7.1.2 | All release-related requirements | Decision authority is available during release window. | Project Management | Production Go-Live | Baselined
7.2.1 | 7.0 Deployment & Hypercare | 7.2 Production Deployment | Application & Integration Deployment | Deployment & Hypercare | Deploy approved application build, integrations, configuration, and infrastructure changes to production. | Production deployment record | Deployment completes per approved cutover plan without unresolved critical deployment failure. | Validation & Deployment Lead | Technology Lead | 7.1.3 | All applicable technical requirements | Required deployment resources are on-call. | Cloud & Infrastructure | Production Go-Live | Baselined
7.2.2 | 7.0 Deployment & Hypercare | 7.2 Production Deployment | Production Verification | Deployment & Hypercare | Execute post-deployment smoke checks, interface checks, monitoring verification, and business confirmation. | Production verification results | Critical workflows, integrations, monitoring, and user access are confirmed operational. | Validation & Deployment Lead | Business Owner | 7.2.1,4.2.4 | BUS-001,INT-001–INT-004,OPS-001 | Production data migration has completed/reconciled. | Cloud & Infrastructure | Production Go-Live | Baselined
7.3.1 | 7.0 Deployment & Hypercare | 7.3 Hypercare & Transition | Hypercare Incident Management | Deployment & Hypercare | Operate structured four-week hypercare with triage, prioritization, ownership, and rapid issue resolution. | Hypercare tracker; Daily/weekly stabilization reports | Production issues are tracked to closure/BAU handover and severity trends remain within exit thresholds. | Validation & Deployment Lead | Operations Lead | 7.2.2 | OPS-001,OPS-002 | Cross-functional support team remains available during hypercare. | Internal / Contract Resources | Hypercare | Baselined
7.3.2 | 7.0 Deployment & Hypercare | 7.3 Hypercare & Transition | Stabilization & Exit Assessment | Deployment & Hypercare | Assess defect/incident trends, performance, operational readiness, and open actions against hypercare exit criteria. | Hypercare Exit Assessment | Exit criteria are met and remaining items have BAU ownership and approved plans. | Validation & Deployment Lead | Business Owner | 7.3.1 | NFR-003,OPS-002 | Operational metrics are available during hypercare. | Internal / Contract Resources | Hypercare Complete | Baselined
7.3.3 | 7.0 Deployment & Hypercare | 7.3 Hypercare & Transition | Operational Handover | Deployment & Hypercare | Transfer support documentation, ownership, known issues, monitoring, recovery procedures, and support obligations to BAU. | Operational Handover Pack; Acceptance | Operations formally accepts support ownership and open items. | Validation & Deployment Lead | Operations Lead | 7.3.2 | OPS-001–OPS-003 | Support team has completed knowledge transfer. | Internal / Contract Resources | Hypercare Complete | Baselined
8.1.1 | 8.0 Project Closure | 8.1 Formal Closure | Final Deliverable Acceptance | Project Closure | Confirm completion and formal acceptance of all approved project deliverables and approved residual items. | Final Acceptance Record | Business and technical acceptance is documented for all project deliverables. | Project Manager | Executive Sponsor | 7.3.3 and all deliverables | All applicable requirements | Residual items have assigned BAU owners. | Project Management | Project Closure | Baselined
8.1.2 | 8.0 Project Closure | 8.1 Formal Closure | Financial & Procurement Closeout | Project Closure | Reconcile final project costs, commitments, purchase orders, vendor deliverables, accruals, and unused reserves. | Financial closeout; Procurement closure | Costs reconcile to final approved budget and commercial obligations are closed or transferred. | Project Manager | Executive Sponsor | Vendor completion and final actuals | N/A | Finance/procurement data is available at close. | Project Management | Project Closure | Baselined
8.1.3 | 8.0 Project Closure | 8.1 Formal Closure | Lessons Learned | Project Closure | Capture delivery, governance, technical, stakeholder, commercial, and operational lessons for reuse. | Lessons Learned Register | Lessons are reviewed with key stakeholders and stored for future reference. | Project Manager | Executive Sponsor | Project completion | N/A | Key team members are available for closure workshop. | Project Management | Project Closure | Baselined
8.1.4 | 8.0 Project Closure | 8.1 Formal Closure | Benefits Measurement Handover | Project Closure | Transfer benefit metrics, owners, measurement cadence, assumptions, and outstanding realization actions to business ownership. | Benefits Handover | Named business owners accept post-project benefit measurement responsibility. | Project Manager | Business Owner | Stable operations and Business Case | BUS-001 and business-case benefits | Benefits continue after project closure. | Project Management | Project Closure | Baselined
8.1.5 | 8.0 Project Closure | 8.1 Formal Closure | Project Closure Report & Approval | Project Closure | Summarize final performance against scope, schedule, budget, quality, risks, benefits handover, and closure criteria. | Project Closure Report; Closure approval | Executive Sponsor approves formal project closure. | Project Manager | Executive Sponsor | 8.1.1–8.1.4 | N/A | All material closure actions have ownership. | Project Management | Project Closure | Baselined

## WBS Summary
Project Atlas — WBS Summary
Control Account | Work Package Count | Share of Work Packages | Primary Cost Category | Work Package Count
1.0 Project Management & Governance | 10 | 15.87% | Project Management | 15
2.0 Requirements & Solution Design | 10 | 15.87% | Internal / Contract Resources | 30
3.0 Application Development | 8 | 12.7% | External / Specialist Vendor Services | 1
4.0 Integration & Data Migration | 8 | 12.7% | Cloud & Infrastructure | 4
5.0 Testing & Validation | 10 | 15.87% | Software & Licensing | 1
6.0 Business Readiness & Training | 4 | 6.349% | Validation & Security Services | 8
7.0 Deployment & Hypercare | 8 | 12.7% | Training & Change Readiness | 4
8.0 Project Closure | 5 | 7.937% | Travel & Operational Costs | 0

## Lists
Workstream | Owner Role | Acceptance Authority | Cost Category | Status
Project Management & Governance | Project Manager | Executive Sponsor | Project Management | Baselined
Requirements & Solution Design | Business Analysis Lead | Business Owner | Internal / Contract Resources | Planned
Application Development | Application Development Lead | Technology Lead | Internal / Contract Resources | In Progress
Integration & Data Migration | Integration & Data Migration Lead | Technology Lead | Internal / Contract Resources | Complete
Testing & Validation | Validation & Deployment Lead | Quality / Compliance | Validation & Security Services
Business Readiness & Training | Change & Training Lead | Business Owner | Training & Change Readiness
Deployment & Hypercare | Validation & Deployment Lead | Steering Committee | Cloud & Infrastructure
Project Closure | Project Manager | Executive Sponsor | Project Management
|  | Information Security | Software & Licensing
|  | Operations Lead | External / Specialist Vendor Services
Travel & Operational Costs