## Overview
Project Atlas — Integrated Project Schedule
Project | Project Atlas
Artifact | Integrated Project Schedule
Schedule Baseline | Version 1.0
Baseline Start | 2026-01-05
Baseline Finish | 2026-09-30
Delivery Model | Predictive / Waterfall
Baseline Calendar | Monday–Friday standard business-day calendar
Scope Basis | Approved Scope Statement + WBS + WBS Dictionary
Schedule Logic | WBS-linked activities with predecessor relationships and stage-gate milestones
Critical Path | Zero-float sequence driving current project completion
Schedule Control | Variance, float, critical path, milestone impact and integrated change control
Portfolio Note | All dates, durations and dependency data are synthetic.
Schedule KPI | Value | Purpose | Target / Interpretation
Total Schedule Items | 65 | Activities + milestones | Baseline
Milestones | 12 | Formal decision / completion points | Monitor
Critical Items | 37 | Zero-float / critical items | Monitor closely
Baseline Working Days | 193 | Planned business-day span | ~9 months
Baseline Status | Established | Schedule version 1.0 | Established
Next Dependency | Resource Plan | Resource loading follows schedule approval | Commit #9

## Integrated Schedule
Activity ID | WBS ID | Activity / Milestone | Owner | Baseline Start | Baseline Finish | Duration (WD) | Predecessor(s) | Total Float (WD) | Critical? | Status | Type | Baseline % Complete | Forecast Finish | Finish Variance (WD) | Notes
AT-001 | 1.1.1 | Finalize integrated project management approach | Project Manager | 2026-01-05 | 2026-01-09 | 5 |  | 5 | No | Not Started | Activity | 0% | 2026-01-09 | 0 | Establish detailed planning approach following Charter approval.
AT-002 | 1.2.3 | Project Charter approval milestone | Executive Sponsor | 2026-01-09 | 2026-01-09 | 1 | AT-001 | 0 | Yes | Not Started | Milestone | 0% | 2026-01-09 | 0 | Formal authorization to proceed.
AT-010 | 2.1.1 | Business and functional requirements workshops | Business Analysis Lead | 2026-01-12 | 2026-01-30 | 15 | AT-002 | 0 | Yes | Not Started | Activity | 0% | 2026-01-30 | 0 | Core workflow and functional requirements.
AT-011 | 2.1.2 | Integration and data requirements definition | Business Analysis Lead | 2026-01-19 | 2026-02-03 | 12 | AT-002 | 3 | No | Not Started | Activity | 0% | 2026-02-03 | 0 | Four interfaces and migration requirements.
AT-012 | 2.1.3 | Regulatory, security and NFR definition | Business Analysis Lead | 2026-01-19 | 2026-02-03 | 12 | AT-002 | 3 | No | Not Started | Activity | 0% | 2026-02-03 | 0 | Compliance, security, operations, performance and training requirements.
AT-013 | 2.1.4 | Requirements traceability and review | Business Analysis Lead | 2026-02-02 | 2026-02-06 | 5 | AT-010,AT-011,AT-012 | 0 | Yes | Not Started | Activity | 0% | 2026-02-06 | 0 | Complete RTM and resolve review comments.
AT-014 | 2.1.4 | Requirements baseline approved | Business Owner | 2026-02-06 | 2026-02-06 | 1 | AT-013 | 0 | Yes | Not Started | Milestone | 0% | 2026-02-06 | 0 | Requirements stage gate.
AT-020 | 2.2.1 | Application solution design | Solution Architect | 2026-02-09 | 2026-02-27 | 15 | AT-014 | 0 | Yes | Not Started | Activity | 0% | 2026-02-27 | 0 | Application architecture, workflows, reporting and audit design.
AT-021 | 2.2.2 | Integration solution design | Integration & Data Migration Lead | 2026-02-09 | 2026-02-24 | 12 | AT-014 | 4 | No | Not Started | Activity | 0% | 2026-02-24 | 0 | Patterns, mappings, error handling and monitoring.
AT-022 | 2.2.3 | Data migration design | Integration & Data Migration Lead | 2026-02-16 | 2026-03-02 | 11 | AT-014 | 3 | No | Not Started | Activity | 0% | 2026-03-02 | 0 | Mapping, transformation and reconciliation design.
AT-023 | 2.2.4 | Security and access design | Solution Architect | 2026-02-16 | 2026-02-27 | 10 | AT-014 | 2 | No | Not Started | Activity | 0% | 2026-02-27 | 0 | RBAC, authentication, encryption and logging.
AT-024 | 2.2.5 | Operational and support design | Solution Architect | 2026-02-23 | 2026-03-03 | 7 | AT-020 | 4 | No | Not Started | Activity | 0% | 2026-03-03 | 0 | Monitoring, recovery and support model.
AT-025 | 2.2.6 | Consolidated design review and closure | Solution Architect | 2026-03-02 | 2026-03-06 | 5 | AT-020,AT-021,AT-022,AT-023,AT-024 | 0 | Yes | Not Started | Activity | 0% | 2026-03-06 | 0 | Resolve mandatory design comments.
AT-026 | 2.2.6 | Solution design approved | Technology Lead | 2026-03-06 | 2026-03-06 | 1 | AT-025 | 0 | Yes | Not Started | Milestone | 0% | 2026-03-06 | 0 | Design stage gate.
AT-030 | 3.1.1 | Application framework and base configuration | Application Development Lead | 2026-03-09 | 2026-03-27 | 15 | AT-026 | 0 | Yes | Not Started | Activity | 0% | 2026-03-27 | 0 | Foundation and common services.
AT-031 | 3.1.2 | Role-based access implementation | Application Development Lead | 2026-03-23 | 2026-04-10 | 15 | AT-030,AT-023 | 5 | No | Not Started | Activity | 0% | 2026-04-10 | 0 | RBAC and IAM-related application configuration.
AT-032 | 3.2.1 | Core record management workflow development | Application Development Lead | 2026-03-30 | 2026-04-17 | 15 | AT-030 | 0 | Yes | Not Started | Activity | 0% | 2026-04-17 | 0 | Create/review/update/submit workflow.
AT-033 | 3.2.2 | Approval routing and business rules development | Application Development Lead | 2026-04-06 | 2026-04-24 | 15 | AT-032 | 0 | Yes | Not Started | Activity | 0% | 2026-04-24 | 0 | Approval logic and state transitions.
AT-034 | 3.2.3 | Search, reporting and audit feature development | Application Development Lead | 2026-04-06 | 2026-04-24 | 15 | AT-032 | 5 | No | Not Started | Activity | 0% | 2026-04-24 | 0 | Search, reports and audit functions.
AT-035 | 3.2.4 | Workflow notification feature development | Application Development Lead | 2026-04-20 | 2026-05-01 | 10 | AT-033,AT-021 | 4 | No | Not Started | Activity | 0% | 2026-05-01 | 0 | Application-side event triggering.
AT-036 | 3.3.1 | Developer verification and code-quality remediation | Application Development Lead | 2026-04-27 | 2026-05-06 | 8 | AT-031,AT-033,AT-034,AT-035 | 0 | Yes | Not Started | Activity | 0% | 2026-05-06 | 0 | Developer testing and quality checks.
AT-037 | 3.3.2 | Package application release candidate | Application Development Lead | 2026-05-07 | 2026-05-08 | 2 | AT-036 | 0 | Yes | Not Started | Activity | 0% | 2026-05-08 | 0 | Controlled build for formal testing.
AT-038 | 3.3.2 | Application build complete | Technology Lead | 2026-05-08 | 2026-05-08 | 1 | AT-037 | 0 | Yes | Not Started | Milestone | 0% | 2026-05-08 | 0 | Application build completion.
AT-040 | 4.1.1 | IAM integration build | Integration & Data Migration Lead | 2026-03-16 | 2026-04-03 | 15 | AT-021,AT-023 | 5 | No | Not Started | Activity | 0% | 2026-04-03 | 0 | Enterprise IAM interface.
AT-041 | 4.1.2 | Master Data integration build | Integration & Data Migration Lead | 2026-03-16 | 2026-04-10 | 20 | AT-021 | 5 | No | Not Started | Activity | 0% | 2026-04-10 | 0 | Master/reference data integration.
AT-042 | 4.1.3 | Records Management integration build | Integration & Data Migration Lead | 2026-03-23 | 2026-04-17 | 20 | AT-021 | 3 | No | Not Started | Activity | 0% | 2026-04-17 | 0 | Records/archive integration.
AT-043 | 4.1.4 | Notification integration build | Integration & Data Migration Lead | 2026-04-06 | 2026-05-01 | 20 | AT-021 | 4 | No | Not Started | Activity | 0% | 2026-05-01 | 0 | Enterprise notification interface.
AT-044 | 4.1 | Integration component verification | Integration & Data Migration Lead | 2026-05-04 | 2026-05-08 | 5 | AT-040,AT-041,AT-042,AT-043 | 0 | Yes | Not Started | Activity | 0% | 2026-05-08 | 0 | Confirm interfaces ready for formal integration testing.
AT-045 | 4.1 | Integration build complete | Technology Lead | 2026-05-08 | 2026-05-08 | 1 | AT-044 | 0 | Yes | Not Started | Milestone | 0% | 2026-05-08 | 0 | Four interfaces ready for formal testing.
AT-046 | 4.2.1 | Source data profiling and mapping | Integration & Data Migration Lead | 2026-02-16 | 2026-03-06 | 15 | AT-014 | 10 | No | Not Started | Activity | 0% | 2026-03-06 | 0 | Assess migration scope and data quality.
AT-047 | 4.2.2 | Migration routines and reconciliation controls | Integration & Data Migration Lead | 2026-03-09 | 2026-04-24 | 35 | AT-022,AT-046 | 5 | No | Not Started | Activity | 0% | 2026-04-24 | 0 | Develop migration code and controls.
AT-048 | 4.2.3 | Trial migration preparation | Integration & Data Migration Lead | 2026-04-27 | 2026-05-08 | 10 | AT-047 | 5 | No | Not Started | Activity | 0% | 2026-05-08 | 0 | Prepare extracts, environment and control totals.
AT-049 | 4.2.3 | Execute trial migration and reconciliation | Integration & Data Migration Lead | 2026-05-11 | 2026-05-22 | 10 | AT-048 | 5 | No | Not Started | Activity | 0% | 2026-05-22 | 0 | Validate migration logic and timing.
AT-050 | 5.1.1 | Develop test and validation strategy | Validation & Deployment Lead | 2026-03-23 | 2026-04-10 | 15 | AT-026 | 10 | No | Not Started | Activity | 0% | 2026-04-10 | 0 | Test levels, evidence and governance.
AT-051 | 5.1.2 | Prepare test cases and traceability | Validation & Deployment Lead | 2026-04-13 | 2026-05-01 | 15 | AT-050,AT-014 | 5 | No | Not Started | Activity | 0% | 2026-05-01 | 0 | Trace test coverage to RTM.
AT-052 | 5.1.2 | Test environment and data readiness | Validation & Deployment Lead | 2026-04-27 | 2026-05-08 | 10 | AT-050 | 0 | Yes | Not Started | Activity | 0% | 2026-05-08 | 0 | Environment readiness for formal testing.
AT-053 | 5.2.1 | System and regression testing | Validation & Deployment Lead | 2026-05-11 | 2026-06-05 | 20 | AT-038,AT-052 | 0 | Yes | Not Started | Activity | 0% | 2026-06-05 | 0 | Formal application verification.
AT-054 | 5.2.2 | Integration testing | Validation & Deployment Lead | 2026-05-18 | 2026-06-12 | 20 | AT-045,AT-052 | 0 | Yes | Not Started | Activity | 0% | 2026-06-12 | 0 | End-to-end interface scenarios.
AT-055 | 5.2.3 | Performance testing | Validation & Deployment Lead | 2026-06-08 | 2026-06-19 | 10 | AT-053 | 5 | No | Not Started | Activity | 0% | 2026-06-19 | 0 | Concurrency and response-time testing.
AT-056 | 5.2.4 | Security assessment | Validation & Deployment Lead | 2026-06-08 | 2026-06-19 | 10 | AT-053,AT-054 | 0 | Yes | Not Started | Activity | 0% | 2026-06-19 | 0 | Security controls and vulnerability assessment.
AT-057 | 5.2 | Technical testing complete | Technology Lead | 2026-06-19 | 2026-06-19 | 1 | AT-053,AT-054,AT-055,AT-056 | 0 | Yes | Not Started | Milestone | 0% | 2026-06-19 | 0 | Technical verification stage gate.
AT-060 | 5.3.1 | Regulated validation execution | Validation & Deployment Lead | 2026-06-22 | 2026-07-10 | 15 | AT-057 | 0 | Yes | Not Started | Activity | 0% | 2026-07-10 | 0 | Execute controlled validation protocols.
AT-061 | 5.3.2 | User Acceptance Testing | Validation & Deployment Lead | 2026-06-22 | 2026-07-17 | 20 | AT-057,AT-049 | 0 | Yes | Not Started | Activity | 0% | 2026-07-17 | 0 | Representative regional business UAT.
AT-062 | 5.3.3 | Defect remediation and retesting | Application Development Lead | 2026-07-06 | 2026-07-24 | 15 | AT-060,AT-061 | 0 | Yes | Not Started | Activity | 0% | 2026-07-24 | 0 | Resolve validation/UAT defects.
AT-063 | 5.3.4 | Final traceability reconciliation and validation approval | Validation & Deployment Lead | 2026-07-27 | 2026-07-31 | 5 | AT-062 | 0 | Yes | Not Started | Activity | 0% | 2026-07-31 | 0 | Reconcile RTM, evidence and approvals.
AT-064 | 5.3 | Validation and UAT complete | Quality / Compliance Lead | 2026-07-31 | 2026-07-31 | 1 | AT-063 | 0 | Yes | Not Started | Milestone | 0% | 2026-07-31 | 0 | Validation and business acceptance gate.
AT-070 | 6.1.1 | Business impact and readiness assessment | Change & Training Lead | 2026-05-18 | 2026-06-12 | 20 | AT-026 | 15 | No | Not Started | Activity | 0% | 2026-06-12 | 0 | Assess impacted roles and readiness gaps.
AT-071 | 6.1.2 | Stakeholder communications and adoption activities | Change & Training Lead | 2026-06-15 | 2026-08-07 | 40 | AT-070 | 10 | No | Not Started | Activity | 0% | 2026-08-07 | 0 | Targeted change communications.
AT-072 | 6.2.1 | Develop training materials and user guidance | Change & Training Lead | 2026-06-08 | 2026-07-10 | 25 | AT-053 | 10 | No | Not Started | Activity | 0% | 2026-07-10 | 0 | Role-based materials.
AT-073 | 6.2.2 | Deliver user training and track completion | Change & Training Lead | 2026-07-13 | 2026-08-07 | 20 | AT-072 | 5 | No | Not Started | Activity | 0% | 2026-08-07 | 0 | Achieve priority-user readiness threshold.
AT-080 | 7.1.2 | Develop cutover and rollback plan | Validation & Deployment Lead | 2026-07-20 | 2026-08-07 | 15 | AT-061 | 5 | No | Not Started | Activity | 0% | 2026-08-07 | 0 | Detailed deployment sequencing and rollback.
AT-081 | 7.1.1 | Production readiness assessment | Validation & Deployment Lead | 2026-08-03 | 2026-08-14 | 10 | AT-064,AT-071,AT-073,AT-080 | 0 | Yes | Not Started | Activity | 0% | 2026-08-14 | 0 | Consolidate quality, technical and business readiness.
AT-082 | 7.1.3 | Go / No-Go approval | Steering Committee | 2026-08-17 | 2026-08-17 | 1 | AT-081 | 0 | Yes | Not Started | Milestone | 0% | 2026-08-17 | 0 | Formal production authorization.
AT-083 | 4.2.4 | Production data migration and reconciliation | Integration & Data Migration Lead | 2026-08-20 | 2026-08-21 | 2 | AT-082,AT-049 | 0 | Yes | Not Started | Activity | 0% | 2026-08-21 | 0 | Production migration within release window.
AT-084 | 7.2.1 | Production application and integration deployment | Validation & Deployment Lead | 2026-08-21 | 2026-08-21 | 1 | AT-082 | 0 | Yes | Not Started | Milestone | 0% | 2026-08-21 | 0 | Production Go-Live.
AT-085 | 7.2.2 | Production verification | Validation & Deployment Lead | 2026-08-24 | 2026-08-24 | 1 | AT-083,AT-084 | 0 | Yes | Not Started | Milestone | 0% | 2026-08-24 | 0 | Confirm critical production workflows and interfaces.
AT-090 | 7.3.1 | Hypercare incident management | Validation & Deployment Lead | 2026-08-24 | 2026-09-18 | 20 | AT-085 | 0 | Yes | Not Started | Activity | 0% | 2026-09-18 | 0 | Four-week structured stabilization period.
AT-091 | 7.3.2 | Hypercare exit assessment | Validation & Deployment Lead | 2026-09-17 | 2026-09-18 | 2 | AT-090 | 0 | Yes | Not Started | Activity | 0% | 2026-09-18 | 0 | Assess exit criteria and residual items.
AT-092 | 7.3.3 | Operational handover | Operations Lead | 2026-09-18 | 2026-09-18 | 1 | AT-091 | 0 | Yes | Not Started | Milestone | 0% | 2026-09-18 | 0 | Formal BAU transition.
AT-100 | 8.1.1 | Confirm final deliverable acceptance | Project Manager | 2026-09-21 | 2026-09-23 | 3 | AT-092 | 0 | Yes | Not Started | Activity | 0% | 2026-09-23 | 0 | Confirm final acceptance and residual ownership.
AT-101 | 8.1.2 | Financial and procurement closeout | Project Manager | 2026-09-21 | 2026-09-25 | 5 | AT-092 | 3 | No | Not Started | Activity | 0% | 2026-09-25 | 0 | Reconcile commitments and commercial closure.
AT-102 | 8.1.3 | Lessons learned workshop and documentation | Project Manager | 2026-09-21 | 2026-09-25 | 5 | AT-092 | 3 | No | Not Started | Activity | 0% | 2026-09-25 | 0 | Capture delivery and governance lessons.
AT-103 | 8.1.4 | Benefits measurement handover | Project Manager | 2026-09-24 | 2026-09-28 | 3 | AT-100 | 0 | Yes | Not Started | Activity | 0% | 2026-09-28 | 0 | Transfer benefits tracking ownership.
AT-104 | 8.1.5 | Prepare project closure report | Project Manager | 2026-09-28 | 2026-09-29 | 2 | AT-100,AT-101,AT-102,AT-103 | 0 | Yes | Not Started | Activity | 0% | 2026-09-29 | 0 | Final performance and closure summary.
AT-105 | 8.1.5 | Project closure approved | Executive Sponsor | 2026-09-30 | 2026-09-30 | 1 | AT-104 | 0 | Yes | Not Started | Milestone | 0% | 2026-09-30 | 0 | Formal project completion.
Formulas:
Duration (WD) = MAX(1,NETWORKDAYS([Baseline Start],[Baseline Finish]))
Finish Variance (WD) = NETWORKDAYS([Baseline Finish],[Forecast Finish])-1

## Milestones
Project Atlas — Baseline Milestones
Milestone ID | WBS ID | Milestone | Baseline Date | Owner | Predecessor(s) | Critical? | Governance Meaning
AT-002 | 1.2.3 | Project Charter approval milestone | 2026-01-09 | Executive Sponsor | AT-001 | Yes | Formal project authorization
AT-014 | 2.1.4 | Requirements baseline approved | 2026-02-06 | Business Owner | AT-013 | Yes | Requirements stage gate
AT-026 | 2.2.6 | Solution design approved | 2026-03-06 | Technology Lead | AT-025 | Yes | Design stage gate
AT-038 | 3.3.2 | Application build complete | 2026-05-08 | Technology Lead | AT-037 | Yes | Application build completion
AT-045 | 4.1 | Integration build complete | 2026-05-08 | Technology Lead | AT-044 | Yes | Integration build completion
AT-057 | 5.2 | Technical testing complete | 2026-06-19 | Technology Lead | AT-053,AT-054,AT-055,AT-056 | Yes | Technical verification stage gate
AT-064 | 5.3 | Validation and UAT complete | 2026-07-31 | Quality / Compliance Lead | AT-063 | Yes | Validation and business acceptance gate
AT-082 | 7.1.3 | Go / No-Go approval | 2026-08-17 | Steering Committee | AT-081 | Yes | Production authorization
AT-084 | 7.2.1 | Production application and integration deployment | 2026-08-21 | Validation & Deployment Lead | AT-082 | Yes | Production Go-Live
AT-085 | 7.2.2 | Production verification | 2026-08-24 | Validation & Deployment Lead | AT-083,AT-084 | Yes | Production verification
AT-092 | 7.3.3 | Operational handover | 2026-09-18 | Operations Lead | AT-091 | Yes | BAU transition
AT-105 | 8.1.5 | Project closure approved | 2026-09-30 | Executive Sponsor | AT-104 | Yes | Formal project completion

## Gantt
Project Atlas — Baseline Gantt (Weekly View)
Activity ID | WBS ID | Activity / Milestone | Owner | Start | Finish | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
AT-001 | 1.1.1 | Finalize integrated project management approach | Project Manager | 2026-01-05 | 2026-01-09 | bar: 2026-01-05
AT-002 | 1.2.3 | Project Charter approval milestone | Executive Sponsor | 2026-01-09 | 2026-01-09 | bar: 2026-01-05
AT-010 | 2.1.1 | Business and functional requirements workshops | Business Analysis Lead | 2026-01-12 | 2026-01-30 | bar: 2026-01-12 to 2026-01-26
AT-011 | 2.1.2 | Integration and data requirements definition | Business Analysis Lead | 2026-01-19 | 2026-02-03 | bar: 2026-01-19 to 2026-02-02
AT-012 | 2.1.3 | Regulatory, security and NFR definition | Business Analysis Lead | 2026-01-19 | 2026-02-03 | bar: 2026-01-19 to 2026-02-02
AT-013 | 2.1.4 | Requirements traceability and review | Business Analysis Lead | 2026-02-02 | 2026-02-06 | bar: 2026-02-02
AT-014 | 2.1.4 | Requirements baseline approved | Business Owner | 2026-02-06 | 2026-02-06 | bar: 2026-02-02
AT-020 | 2.2.1 | Application solution design | Solution Architect | 2026-02-09 | 2026-02-27 | bar: 2026-02-09 to 2026-02-23
AT-021 | 2.2.2 | Integration solution design | Integration & Data Migration Lead | 2026-02-09 | 2026-02-24 | bar: 2026-02-09 to 2026-02-23
AT-022 | 2.2.3 | Data migration design | Integration & Data Migration Lead | 2026-02-16 | 2026-03-02 | bar: 2026-02-16 to 2026-03-02
AT-023 | 2.2.4 | Security and access design | Solution Architect | 2026-02-16 | 2026-02-27 | bar: 2026-02-16 to 2026-02-23
AT-024 | 2.2.5 | Operational and support design | Solution Architect | 2026-02-23 | 2026-03-03 | bar: 2026-02-23 to 2026-03-02
AT-025 | 2.2.6 | Consolidated design review and closure | Solution Architect | 2026-03-02 | 2026-03-06 | bar: 2026-03-02
AT-026 | 2.2.6 | Solution design approved | Technology Lead | 2026-03-06 | 2026-03-06 | bar: 2026-03-02
AT-030 | 3.1.1 | Application framework and base configuration | Application Development Lead | 2026-03-09 | 2026-03-27 | bar: 2026-03-09 to 2026-03-23
AT-031 | 3.1.2 | Role-based access implementation | Application Development Lead | 2026-03-23 | 2026-04-10 | bar: 2026-03-23 to 2026-04-06
AT-032 | 3.2.1 | Core record management workflow development | Application Development Lead | 2026-03-30 | 2026-04-17 | bar: 2026-03-30 to 2026-04-13
AT-033 | 3.2.2 | Approval routing and business rules development | Application Development Lead | 2026-04-06 | 2026-04-24 | bar: 2026-04-06 to 2026-04-20
AT-034 | 3.2.3 | Search, reporting and audit feature development | Application Development Lead | 2026-04-06 | 2026-04-24 | bar: 2026-04-06 to 2026-04-20
AT-035 | 3.2.4 | Workflow notification feature development | Application Development Lead | 2026-04-20 | 2026-05-01 | bar: 2026-04-20 to 2026-04-27
AT-036 | 3.3.1 | Developer verification and code-quality remediation | Application Development Lead | 2026-04-27 | 2026-05-06 | bar: 2026-04-27 to 2026-05-04
AT-037 | 3.3.2 | Package application release candidate | Application Development Lead | 2026-05-07 | 2026-05-08 | bar: 2026-05-04
AT-038 | 3.3.2 | Application build complete | Technology Lead | 2026-05-08 | 2026-05-08 | bar: 2026-05-04
AT-040 | 4.1.1 | IAM integration build | Integration & Data Migration Lead | 2026-03-16 | 2026-04-03 | bar: 2026-03-16 to 2026-03-30
AT-041 | 4.1.2 | Master Data integration build | Integration & Data Migration Lead | 2026-03-16 | 2026-04-10 | bar: 2026-03-16 to 2026-04-06
AT-042 | 4.1.3 | Records Management integration build | Integration & Data Migration Lead | 2026-03-23 | 2026-04-17 | bar: 2026-03-23 to 2026-04-13
AT-043 | 4.1.4 | Notification integration build | Integration & Data Migration Lead | 2026-04-06 | 2026-05-01 | bar: 2026-04-06 to 2026-04-27
AT-044 | 4.1 | Integration component verification | Integration & Data Migration Lead | 2026-05-04 | 2026-05-08 | bar: 2026-05-04
AT-045 | 4.1 | Integration build complete | Technology Lead | 2026-05-08 | 2026-05-08 | bar: 2026-05-04
AT-046 | 4.2.1 | Source data profiling and mapping | Integration & Data Migration Lead | 2026-02-16 | 2026-03-06 | bar: 2026-02-16 to 2026-03-02
AT-047 | 4.2.2 | Migration routines and reconciliation controls | Integration & Data Migration Lead | 2026-03-09 | 2026-04-24 | bar: 2026-03-09 to 2026-04-20
AT-048 | 4.2.3 | Trial migration preparation | Integration & Data Migration Lead | 2026-04-27 | 2026-05-08 | bar: 2026-04-27 to 2026-05-04
AT-049 | 4.2.3 | Execute trial migration and reconciliation | Integration & Data Migration Lead | 2026-05-11 | 2026-05-22 | bar: 2026-05-11 to 2026-05-18
AT-050 | 5.1.1 | Develop test and validation strategy | Validation & Deployment Lead | 2026-03-23 | 2026-04-10 | bar: 2026-03-23 to 2026-04-06
AT-051 | 5.1.2 | Prepare test cases and traceability | Validation & Deployment Lead | 2026-04-13 | 2026-05-01 | bar: 2026-04-13 to 2026-04-27
AT-052 | 5.1.2 | Test environment and data readiness | Validation & Deployment Lead | 2026-04-27 | 2026-05-08 | bar: 2026-04-27 to 2026-05-04
AT-053 | 5.2.1 | System and regression testing | Validation & Deployment Lead | 2026-05-11 | 2026-06-05 | bar: 2026-05-11 to 2026-06-01
AT-054 | 5.2.2 | Integration testing | Validation & Deployment Lead | 2026-05-18 | 2026-06-12 | bar: 2026-05-18 to 2026-06-08
AT-055 | 5.2.3 | Performance testing | Validation & Deployment Lead | 2026-06-08 | 2026-06-19 | bar: 2026-06-08 to 2026-06-15
AT-056 | 5.2.4 | Security assessment | Validation & Deployment Lead | 2026-06-08 | 2026-06-19 | bar: 2026-06-08 to 2026-06-15
AT-057 | 5.2 | Technical testing complete | Technology Lead | 2026-06-19 | 2026-06-19 | bar: 2026-06-15
AT-060 | 5.3.1 | Regulated validation execution | Validation & Deployment Lead | 2026-06-22 | 2026-07-10 | bar: 2026-06-22 to 2026-07-06
AT-061 | 5.3.2 | User Acceptance Testing | Validation & Deployment Lead | 2026-06-22 | 2026-07-17 | bar: 2026-06-22 to 2026-07-13
AT-062 | 5.3.3 | Defect remediation and retesting | Application Development Lead | 2026-07-06 | 2026-07-24 | bar: 2026-07-06 to 2026-07-20
AT-063 | 5.3.4 | Final traceability reconciliation and validation approval | Validation & Deployment Lead | 2026-07-27 | 2026-07-31 | bar: 2026-07-27
AT-064 | 5.3 | Validation and UAT complete | Quality / Compliance Lead | 2026-07-31 | 2026-07-31 | bar: 2026-07-27
AT-070 | 6.1.1 | Business impact and readiness assessment | Change & Training Lead | 2026-05-18 | 2026-06-12 | bar: 2026-05-18 to 2026-06-08
AT-071 | 6.1.2 | Stakeholder communications and adoption activities | Change & Training Lead | 2026-06-15 | 2026-08-07 | bar: 2026-06-15 to 2026-08-03
AT-072 | 6.2.1 | Develop training materials and user guidance | Change & Training Lead | 2026-06-08 | 2026-07-10 | bar: 2026-06-08 to 2026-07-06
AT-073 | 6.2.2 | Deliver user training and track completion | Change & Training Lead | 2026-07-13 | 2026-08-07 | bar: 2026-07-13 to 2026-08-03
AT-080 | 7.1.2 | Develop cutover and rollback plan | Validation & Deployment Lead | 2026-07-20 | 2026-08-07 | bar: 2026-07-20 to 2026-08-03
AT-081 | 7.1.1 | Production readiness assessment | Validation & Deployment Lead | 2026-08-03 | 2026-08-14 | bar: 2026-08-03 to 2026-08-10
AT-082 | 7.1.3 | Go / No-Go approval | Steering Committee | 2026-08-17 | 2026-08-17 | bar: 2026-08-17
AT-083 | 4.2.4 | Production data migration and reconciliation | Integration & Data Migration Lead | 2026-08-20 | 2026-08-21 | bar: 2026-08-17
AT-084 | 7.2.1 | Production application and integration deployment | Validation & Deployment Lead | 2026-08-21 | 2026-08-21 | bar: 2026-08-17
AT-085 | 7.2.2 | Production verification | Validation & Deployment Lead | 2026-08-24 | 2026-08-24 | bar: 2026-08-24
AT-090 | 7.3.1 | Hypercare incident management | Validation & Deployment Lead | 2026-08-24 | 2026-09-18 | bar: 2026-08-24 to 2026-09-14
AT-091 | 7.3.2 | Hypercare exit assessment | Validation & Deployment Lead | 2026-09-17 | 2026-09-18 | bar: 2026-09-14
AT-092 | 7.3.3 | Operational handover | Operations Lead | 2026-09-18 | 2026-09-18 | bar: 2026-09-14
AT-100 | 8.1.1 | Confirm final deliverable acceptance | Project Manager | 2026-09-21 | 2026-09-23 | bar: 2026-09-21
AT-101 | 8.1.2 | Financial and procurement closeout | Project Manager | 2026-09-21 | 2026-09-25 | bar: 2026-09-21
AT-102 | 8.1.3 | Lessons learned workshop and documentation | Project Manager | 2026-09-21 | 2026-09-25 | bar: 2026-09-21
AT-103 | 8.1.4 | Benefits measurement handover | Project Manager | 2026-09-24 | 2026-09-28 | bar: 2026-09-21 to 2026-09-28
AT-104 | 8.1.5 | Prepare project closure report | Project Manager | 2026-09-28 | 2026-09-29 | bar: 2026-09-28
AT-105 | 8.1.5 | Project closure approved | Executive Sponsor | 2026-09-30 | 2026-09-30 | bar: 2026-09-28

## Lists
Status | Activity Type | Critical | Owner
Not Started | Activity | Yes | Project Manager
In Progress | Milestone | No | Executive Sponsor
Complete |  |  | Business Owner
On Hold |  |  | Technology Lead
Solution Architect
Business Analysis Lead
Application Development Lead
Integration & Data Migration Lead
Validation & Deployment Lead