## Overview
PROJECT ATLAS ¦ Stakeholder Management
Version 1.0 • Synthetic example • M1 (Initiation)
STAKEHOLDERS | COUNT | POWER–INTEREST RESPONSE | COUNT | OWNER
Identified roles | 18 | Manage closely | 9 | Named engagement owner in register
Manage closely | 9 | Keep satisfied | 3 | Named engagement owner in register
Open engagement gaps | 17 | Keep informed | 5 | Named engagement owner in register
|  | Monitor | 1 | Named engagement owner in register
HOW TO USE
1. Review Stakeholder Register and validate role, power, interest, engagement state and owner.
2. Use priority categories to allocate engagement effort; high power + high interest = manage closely.
3. Review engagement gaps and execute the actions in Engagement Plan.
4. Reassess at major gates and after material scope, organization, or risk changes.
5. Public portfolio version: role-based and synthetic. Real engagement assessments are restricted.

## Stakeholder Register
PROJECT ATLAS ¦ Stakeholder Register
Simulation • M1, after charter approval • Version 1.0 • All roles and assessments synthetic
Public, role-based portfolio demonstration only. Do not add real names, contacts, or confidential stakeholder assessments.
ID | Stakeholder / Role | Group | Region | Project interest / responsibility | Power (1–5) | Interest (1–5) | Priority | Current engagement | Target engagement | Engagement owner | Principal concern | Stage-gate / decision touchpoint | Engagement gap
ST-01 | Executive Sponsor | Executive | Global | Strategic outcomes, funding and major decisions | 5 | 5 | Manage closely | Supportive | Leading | Project Manager | Benefits realization; cost and schedule exposure | Charter, Steering Committee, investment and go/no-go | 1
ST-02 | Business Owner | Business | US / UK | Business outcomes, requirements, UAT and benefits ownership | 5 | 5 | Manage closely | Supportive | Leading | Project Manager | Workflow continuity and business acceptance | Requirements baseline, UAT and benefits handover | 1
ST-03 | Technology Director | Technology | Global | Technology capacity, technical direction and readiness | 5 | 4 | Manage closely | Supportive | Leading | Project Manager | Solution supportability and resource conflicts | Architecture/design, capacity and release readiness | 1
ST-04 | Quality & Compliance Lead | Compliance | Global | Validation strategy, traceability and regulated controls | 5 | 5 | Manage closely | Neutral | Leading | Validation & QA Lead | Validation evidence and compliant release | Validation strategy, validation exit and release sign-off | 1
ST-05 | Project Manager | PMO | India / Global | Integrated plan, cost, RAID, change and coordination | 4 | 5 | Manage closely | Leading | Leading | Executive Sponsor | Timely decisions and balanced delivery constraints | All stage-gate recommendations and governance | 0
ST-06 | Solution Architect | Technology | India | Design integrity and cross-system architecture | 4 | 5 | Manage closely | Supportive | Leading | Project Manager | Architecture fit, nonfunctional requirements | Design approval and production readiness | 1
ST-07 | Application Development Lead | Delivery | India | Application build, technical quality and fixes | 3 | 5 | Keep informed | Supportive | Leading | Project Manager | Build capacity and requirements stability | Build completion and defect triage | 1
ST-08 | Integration & Migration Lead | Delivery | India | Four interfaces, mapping and migration quality | 4 | 5 | Manage closely | Supportive | Leading | Project Manager | Interface dependencies and source-data quality | Integration/SIT exit and migration rehearsal | 1
ST-09 | Validation & QA Lead | Quality | India | Test execution, defects and requirements traceability | 4 | 5 | Manage closely | Supportive | Leading | Project Manager | Test coverage, defect closure and evidence | SIT exit, validation exit and release readiness | 1
ST-10 | Business SME / UAT Lead | Business | UK | Scenario validation and representative user acceptance | 3 | 5 | Keep informed | Neutral | Supportive | Business Owner | UAT time allocation and critical workflows | Requirements workshops and UAT sign-off | 1
ST-11 | Information Security Lead | Security | Global | Security assessment and release controls | 5 | 3 | Keep satisfied | Neutral | Supportive | Technology Director | Vulnerabilities, access and security findings | Security assessment and readiness sign-off | 1
ST-12 | Operations & Service Transition Lead | Operations | India / UK | Monitoring, runbooks, support readiness and handover | 4 | 4 | Manage closely | Neutral | Supportive | Technology Director | Support workload and incomplete handover | Cutover, go-live readiness and hypercare exit | 1
ST-13 | Regional Business Representatives | Business | US / UK / APAC | Regional processes, adoption and deployment impact | 3 | 4 | Keep informed | Neutral | Supportive | Business Owner | Local workflow changes and communication | Requirements validation, training and rollout | 1
ST-14 | Finance Business Partner | Finance | India | Forecasting, expenditure and financial controls | 4 | 3 | Keep satisfied | Neutral | Supportive | Project Manager | Forecast accuracy, invoices and budget tolerance | Monthly cost review and funding decisions | 1
ST-15 | Procurement / Vendor Lead | Procurement | India | Vendor selection, commercial controls and contracts | 3 | 3 | Monitor | Neutral | Supportive | Project Manager | Procurement lead times and contractual scope | Vendor onboarding and contract changes | 1
ST-16 | External Validation Vendor Lead | External Vendor | Global | Independent validation and specialist deliverables | 2 | 4 | Keep informed | Neutral | Supportive | Validation & QA Lead | Clear acceptance criteria and review cycles | Validation plan and vendor deliverable acceptance | 1
ST-17 | Change & Training Lead | Business Change | India | Training, adoption and communication material | 2 | 5 | Keep informed | Supportive | Leading | Business Owner | User readiness and training completion | Training approval and business readiness | 1
ST-18 | Data Governance / Privacy Lead | Data Governance | Global | Data use, retention and migration governance | 5 | 3 | Keep satisfied | Neutral | Supportive | Technology Director | Data minimization, reconciliation and retention | Migration design and data-governance sign-off | 1

## Engagement Plan
PROJECT ATLAS ¦ Stakeholder Engagement Plan
Engagement actions correspond to IDs in the Stakeholder Register; cadence is the proposed project approach.
ID | Stakeholder / Role | Priority | Engagement approach / information | Channel / evidence | Cadence | Escalation trigger | Immediate action
ST-01 | Executive Sponsor | Manage closely | Decision-focused executive brief | Steering pack + one-page exception summary | Monthly; urgent exceptions same day | Cost/schedule forecast outside tolerance; blocked gate | Confirm benefit owner and funding guardrails
ST-02 | Business Owner | Manage closely | Joint outcomes and acceptance reviews | Business demos + requirements/UAT decisions | Fortnightly; at acceptance gates | Unresolved high-impact process or acceptance issue | Agree measurable UAT criteria and benefits handover
ST-03 | Technology Director | Manage closely | Technical and resource decision forum | Architecture/dependency review | Weekly during design/build | Critical specialist shortfall or design conflict | Confirm technical capacity and architecture approval path
ST-04 | Quality & Compliance Lead | Manage closely | Early validation co-design | Requirements traceability + validation evidence review | Weekly; each formal gate | Validation gap or missing mandatory evidence | Agree validation evidence checklist before design freeze
ST-05 | Project Manager | Manage closely | Integrated delivery and control | Workstream plans, RAID, EVM and action log | Daily/weekly; monthly steering | Cross-workstream blockage or forecast tolerance breach | Keep baseline and decision log current
ST-06 | Solution Architect | Manage closely | Architecture working sessions | Design decisions and integration diagrams | Weekly through design/build | Nonfunctional requirement or design exception | Baseline solution architecture and design assumptions
ST-07 | Application Development Lead | Keep informed | Build planning and blocker removal | Work-package board + defect review | Twice weekly during build | Critical-path slippage or unresolved blocker | Confirm build estimates and handoffs to SIT
ST-08 | Integration & Migration Lead | Manage closely | Interface and migration dependency reviews | Interface tracker + reconciliation samples | Weekly; more often at SIT/cutover | Missing test endpoint, extract or poor migration quality | Secure interface commitments and migration rehearsal
ST-09 | Validation & QA Lead | Manage closely | Test/validation controls and reporting | RTM, test summary and defects | Weekly; daily near quality gates | Severity-1 defect or mandatory test evidence missing | Agree exit criteria and evidence ownership
ST-10 | Business SME / UAT Lead | Keep informed | Time-boxed business walkthroughs | Scenario reviews + UAT progress summary | Fortnightly; daily during UAT | Business users unavailable or acceptance blocked | Book UAT participants and confirm representative scenarios
ST-11 | Information Security Lead | Keep satisfied | Targeted security consultations | Threat/risk assessment + finding register | At design and pre-go-live; exceptions as needed | Critical security finding or late control change | Confirm security assessment window and sign-off criteria
ST-12 | Operations & Service Transition Lead | Manage closely | Operational readiness co-planning | Runbook, monitoring and handover checklist | Fortnightly from build; daily at cutover | Missing runbook or unresolved support ownership | Agree support model, transition criteria and hypercare rota
ST-13 | Regional Business Representatives | Keep informed | Region-specific change briefings | Regional impact and FAQ updates | Monthly; at training and rollout | Regional process mismatch or adoption blocker | Nominate regional SMEs and training contacts
ST-14 | Finance Business Partner | Keep satisfied | Budget and forecast review | Cost baseline, actuals, EAC and invoice summary | Monthly; on material change | Forecast overrun or unapproved commitment | Confirm actual-cost feed and reserve-control process
ST-15 | Procurement / Vendor Lead | Monitor | Early procurement engagement | SOW, lead-time and purchase order tracker | At sourcing milestones; fortnightly if active | Vendor delay or change to contracted deliverables | Lock vendor lead times and acceptance criteria
ST-16 | External Validation Vendor Lead | Keep informed | Deliverable-based vendor coordination | Milestones, evidence and issue tracker | Weekly during validation | Late evidence or failed deliverable acceptance | Agree validation deliverables and review turnaround
ST-17 | Change & Training Lead | Keep informed | Adoption planning with business leads | Training plan + readiness survey | Monthly; weekly before go-live | Training coverage or adoption gap | Define audiences, materials and readiness indicators
ST-18 | Data Governance / Privacy Lead | Keep satisfied | Early data-control assessment | Data inventory, mapping and retention decisions | At migration design and cutover gates | Privacy concern or reconciliation failure | Confirm sensitive data controls and retention rules

## Assessment Guide
PROJECT ATLAS ¦ Assessment Guide
Qualitative ratings are simulated; decision rights are defined separately in Governance-Model.md.
DIMENSION | VALUE | GUIDANCE
Power | 1 | Minimal ability to alter outcomes or release decisions
Power | 3 | Can materially influence a workstream or delivery decision
Power | 5 | Formal authority over funding, acceptance, compliance, or gate outcome
Interest | 1 | Limited involvement or impact
Interest | 3 | Periodic engagement or discrete gate concern
Interest | 5 | Direct, ongoing impact on project delivery or outcomes
Engagement | Unaware | Not yet aware of the project or its implications
Engagement | Resistant | Opposed to the change or proposed approach
Engagement | Neutral | Aware, not yet actively supporting
Engagement | Supportive | Participates constructively
Engagement | Leading | Actively champions or facilitates outcomes
POWER–INTEREST SEGMENT | RULE | INTENDED APPROACH
Manage closely | Power ≥4, interest ≥4 | Frequent two-way involvement and early decisions
Keep satisfied | Power ≥4, interest ≤3 | Targeted reviews; consult at relevant decisions
Keep informed | Power ≤3, interest ≥4 | Regular updates and opportunity for feedback
Monitor | Power ≤3, interest ≤3 | Proportionate, event-driven communication